## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Action Plan
| Table 1 | Action Plan
Settings
| Table 1 | Settings

## Action Plan
Group 2
Project Name - Hospital Database in MS Access and MySQL
Project Summary - create hospital database &
Repository in Git Hub.
ACTION PLAN
ACTION | RESPONSIBLE | PRIORITY | STATUS | START DATE | END DATE | NOTES
GOAL #1 Git Hub repository
Creating the GitHub repository | Nada | High | Complete | 2nd Jan | 3rd Jan | To accept invite as contributors.
GOAL #2 ERD for database
Creating the Entity Relationship Diagram | Dhia | High | Complete | 2nd Jan | 8th Jan | All relationships agreed in database hospitals.
Review ERD relationships as per brief | Dhia, Chetak,Nick, Jiaqi,Nada | Medium | Complete | 2nd Jan | 8th Jan | All primary and foreign keys agreed.
GOAL #3 Database and Query
Creating the DB (MS Access Platform) | Dhia, Nick | High | Complete | 2nd Jan | 9th Jan | MS access database finalised
Creating the DB (My SQL Platform) | Chetak, Jiaqi | High | Complete | 2nd Jan | 12th Jan | Query generated/database upload repository
Generating the MS Access Query | Dhia,Nick, Nada | High | Complete | 9th Jan | 15th Jan | Query generated in MS Access
Generating the MySQL Query | Chetak, Jiaqi | High | Complete | 9th Jan | 12th Jan | Query generated in VS Code and checked on MYSQL
GOAL #4 Read me /Index repository Github
Read me and index page on github | Jiaqi,Nada | Medium | Complete | 2nd Jan | 16th Jan | None
GOAL #5 Generate data for tables
Generated random data for tables as suggested in brief | Dhia | Medium | Complete | 2nd Jan | 5th Jan | Finalised data/any amendment to agree if required.
GOAL # 6 Update all files on Github repository
Add Mysql files via Git Push | Chetak, Jiaqi | High | Complete | 12th Jan | 13th Jan | No issues
Add MS Access files via Git Push | Dhia, Nick | High | Complete | 12th Jan | 16th Jan
Add Group Meeting, Agenda, Action Plan via Git Push | Nada | Medium | Complete | 15th jan | 16th Jan | All meeting file to upload.

## Settings
PRIORITY OPTIONS | PROGRESS OPTIONS
High | Complete
Medium | On Hold
Low | In Progress
Not Started